## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1.1.1 | Login with Booking Number | As a passenger, I want to use my booking number to retrieve my flight booking information, So that I can check my flight information easily. | 1 | 1 | - Verify that when users input their booking numbers, the screen displays information of their flight. |  | 2022-03-18 | 2022-03-24
1.1.3 | Seat Selection | As a passenger, I want select seats in flight. So that I can have a suitable seat. | 1 | 1 | - Verify that upon successful retrieval of the booking, the system will show a summary of the booked flight. - Verify that flight passengers can choose seats they like. |  | 2022-03-19 | 2022-03-21
1.1.4 | Food Selection | As a passenger, I want to select food without breaking taboos ( such as standard, vegetarian, halal, etc.) So that I can have more suitable meat with personal dietary habit. | 1 | 1 | - Verify that upon successful retrieval of the booking, the system will show a summary of the booked flight. - Verify that flight passengers can choose which food does they want when they will in flight.The optional can be standard, vegetarian, halal, etc. |  | 2022-03-19 | 2022-03-23
1.1.5 | Confirmation | As a passenger, I want scan my ID documents, So that I can click to confirm the check-in | 1 | 1 | - Verify that after choosing seats and food, the screen shows the passengers to scan their ID documents to conform they will check in. |  | 2022-03-29 | 2022-03-29
1.3.1 | Paper Boarding Pass | As a traditional passenger, I want a paper characteristics boarding pass So that I can get clear information without going through the tedious process of looking it up on my phone | 1 | 1 | - Verify that the boarding pass has information including flight number, airlines, destination, class level, flight date, seat number, boarding gate, passenger name, boarding time and the ID of the boarding pass - Verify that the layout is reasonable and beautiful |  | 2022-03-20 | 2022-03-20
1.2.3 | Bill Confirmation | As a Passenger with special needs I want to clearly see my extra payment list So that I can pay for that with no doubt | 2 | 1 | - Verify that the list is displayed wholly. - Verify that the list is displayed clearly. - Verify the process of paying is convenient. |  | 2022-03-23 | 2022-03-26
1.3.3.1 | Printing baggage tickets | As an airport staff I want a ticket that needs to be attached to the check-in baggage So that I can record and check the weight and contents of the luggage during the security check to ensure the safety of the flight | 2 | 1 | - Verify that the ticket has the information including the flight number, destination, departure, and the ID of the baggage tag - Verify that the layout is reasonable and beautiful |  | 2022-03-22 | 2022-03-24
1.3.3.2 | Printing baggage tickets | As a Businessman I want a ticket with the number of the assigned bag drop counter where the passenger needs to go to drop his/her check-in baggage So that I can faster access to bag drop counter information | 2 | 1 | - Verify that tickets are printed with adhesive material on the back, giving passengers the option to attach their tickets to their boarding passes without losing them |  | 2022-03-22 | 2022-03-24
1.1.2 | Login with ID | As a passenger, I want to have multiple ways to retrieve my flight booking information, So that I can continue even if I forget my booking number. | 3 | 1 | - Verify that users have the options to search their flight information in ways other than inputting booking number, such as entering surname and ID number, or scanning their ID documents. |  | 2022-03-22 | 2022-03-28
1.2.1 | Seat preferences | As a Passenger with special seating needs I want to select special seat (e.g., seat with extra legroom) So that I can stay more comfortable during the flight | 3 | 1 | - Verify that seats that can be chosen are still available. - Verify that user can see the position of seat clearly. - Verify that the additional price can be displayed. |  | 2022-03-19 | 2022-03-21
1.3.2 | Printing tags | As a passenger with a plain suitcase I want a tag that needs to be attached to the carry-on baggage So that I can find my own luggage by checking the tag on my suitcase, and the baggage won’t be taken in error | 3 | 1 | - Verify that the tag has the information including the surname of the passenger and the number of the baggage |  | 2022-03-22 | 2022-03-23
1.4 | Back-end system | As an Airline staff I want to view the list of passengers and their check-in status So that I can provide info to other departments | 3 | 1 | - Verify that the page can display real-time status. - Verify that passengers that have not checked in yet are listed on top. - Verify that special needs of passengers are attached. |  | 2022-03-25 | 2022-03-27
1.2.2 | Meal preferences | As a Passenger with special meal needs I want to select special meal (e.g., Chinese food, French food…) So that I can eat more delicious food during flight | 4 | 1 | - Verify that meal that can be chosen are available for that Airline company - Verify that sample pictures can be displayed - Verify that the additional price can be displayed. |  | 2022-03-19 | 2022-03-23
2.1 | Add I/O port config | As an airport staff I want to config the I/O port of card reader mounted on kiosk So that I can choose devices more flexible | 2 | 2 | - Verify that configuration file should be generated if not exists - Verify that user can edit configuration file |  | 2022-04-08 | 2022-04-11
2.2 | Better admin exit | As an airport staff I want to make sure that I can and only I can exit this software So that the check-in system can run in safe environment | 1 | 2 | - Verify that the software should be killed at any circumstances - Verify that the method is hidden on screen |  | 2022-04-11 | 2022-04-11
2.3 | Show all filghts | As a passenger I want to select flights from multiple booking numbers So that I can check in any flight I booked | 2 | 2 | - Verify that all flights are displayed correctly - Verify that flight info card is categorized by booking numbers |  | 2022-04-10 | 2022-04-10
2.4 | Add planes info | As a passenger I want to know plane information when selecting seats So that I can choose the seat I like | 3 | 2 | - Verify that model, capacity and airline are included |  | 2022-04-11 | 2022-04-11
2.5 | Add animation | As an airport manager I want to equip the software with fancy animations So that my passengers can have silky smooth experience | 2 | 2 | - Verify that no bug occur - Verify that the animation can run like silky chocolate |  | 2022-04-11 | 2022-04-11
2.6 | Add clock | As a passenger I want to know the current time when I use the software So that I can compare time conveniently | 3 | 2 | - Verify that the clock wouldn't stop |  | 2022-04-11 | 2022-04-11
3.1 | Better seat selection page | As an airline staff I want seat selection page to support any seat pattern So that it can display different number of columns of seats | 1 | 3 | - Verify that seat pattern is included in database - Verify that different seat pattern gives different seat display |  | 2022-04-19 | 2022-04-21
3.2 | Disable main when when admin console is called | As an airport staff I want to lock the main frame when admin console is active So that the main programmed is protected | 2 | 3 | - Verify that there is no reponse if click the area out of admin console |  | 2022-04-15 | 2022-04-16
3.3 | Read config from memory | As an airline manager I want my system to be configuration-consistant So that my customers will have a stable environment when they check-in | 2 | 3 | - Verify that whether the system keeps stable when configuration changes |  | 2022-04-18 | 2022-04-19
3.4 | Add exit timer | As an airport manager I want to exit(lock) the software if idle for some time So that energy is saved | 2 | 3 | - Verify that software returns to welcome page after 120 seconds |  | 2022-04-18 | 2022-04-26
3.5 | Better check-in card display logic | As an airline manager I want to prevent passengers from checking in far-furture flights So that we are not disrupted with non-urgent information | 2 | 3 | -Verify that flights in 1 day are not displayed at flight selection page |  | 2022-04-19 | 2022-04-19
3.6 | Add airport name to config | As an airline manager I want pre-store some airports’ names in the configuration So that passengers can easily choose the airport they want to go | 2 | 3 | -Verify that config includes airports’ name |  | 2022-04-20 | 2022-04-20
3.7 | Add custom preferences for different airline companys | As an airline staff I want enable special preference that my company provides So that passengers can use out product | 2 | 3 | - Verify that an interface is provided to load different preference settings - Verify that when settings changes, preferences changes, too |  | 2022-04-23 | 2022-04-23
3.8 | Add animation speed shell to config | As an airline manager I want pre-store multiple mode of animation speed in the configuration So that passengers can satisfy the animation in the system | 2 | 3 | -Verify that config includes different speeds of animation |  | 2022-04-24 | 2022-04-24
3.9 | Add meal preference | As an airport staff I want to be able to choose more meal in better looking pages So that passengers can save time | 2 | 3 | -Verify that meal preference changes according to config settings |  | 2022-04-25 | 2022-04-26
3.1 | Add custom theme color | As an airport staff I want to be able to choose the theme color So that I can use the color that fits the airport | 3 | 3 | - Verify that config includes theme color entry - Verify that theme color changes according to config settings |  | 2022-04-21 | 2022-04-22
4.1 | Should not run if failed to load config | As a airport manager I want the software not to run if it fails to load any configuration items So that service with defect will not be provided to users | 2 | 4 | -Verify that if any configuration entry is missing or invalid, the programme does not launch -Verify that when launch is aborted, admin is informed of problematic entries |  | 2022-05-09 | 2022-05-10
4.2 | Check card numbers | As an airline stuff I want to ensure that the text field can only be accepted 8 digits card number So that card number can be unified | 2 | 4 | -Verify that there will be a warning if the card number is not 8 digits. |  | 2022-05-10 | 2022-05-11
4.3 | Display aircraft information | As a passenger I want to be able to know the aircraft information So that I can make sure I'm checking in the right flight | 3 | 4 | - Verify that aircraft information includes plane model, capacity and airline. - Verify that the aircraft information window is foldable. |  | 2022-05-06 | 2022-05-11
4.4 | Configurable auto dark theme | As an airport staff, I want to decide if the software should change to dark theme when the night falls, So that passengers can have a better check-in experience. | 4 | 4 | - Verify that instance variables change only at the end of a check-in process. - Verify that the theme will reset to the previous light theme the next morning. |  | 2022-05-06 | 2022-05-07
4.5 | Multi-platform DB operator | As an airport manager, I want to check the correctness of the whole program by using tests, and tests should have abilities to run on different OSs. | 4 | 4 | - Verify that tests can run on different OSs |  | 2022-05-07 | 2022-05-08
4.6 | No-operation detection | As an airport manager, I want the program back to the welcome page if no operation at the login page in a fixed time. | 4 | 4 | - Verify that detection is accurate. |  | 2022-05-07 | 2022-05-08
4.7 | Configuration should use less I/O | As a airport manager I want the software only use I/O once when launching the software So that performance is optimized | 4 | 4 | - Verify that I/O operation only happen once when launching software |  | 2022-05-06 | 2022-05-06
4.8 | Animations after pressing "Pay" | As a passenger I want there's an animation in the payment screen So that make sure I finish paying | 4 | 4 | - Verify that animation only appears when done |  | 2022-05-06 | 2022-05-07