## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
1.1.1 | Login with Booking Number | As a passenger, I want to use my booking number to retrieve my flight booking information, So that I can check my flight information easily. | 1 | 1 | - Verify that when users input their booking numbers, the screen displays information of their flight. |  | 2022-03-18 | 2022-03-24
1.1.3 | Seat Selection | As a passenger, I want select seats in flight. So that I can have a suitable seat. | 1 | 1 | - Verify that upon successful retrieval of the booking, the system will show a summary of the booked flight. - Verify that flight passengers can choose seats they like. |  | 2022-03-19 | 2022-03-21
1.1.4 | Food Selection | As a passenger, I want to select food without breaking taboos ( such as standard, vegetarian, halal, etc.) So that I can have more suitable meat with personal dietary habit. | 1 | 1 | - Verify that upon successful retrieval of the booking, the system will show a summary of the booked flight. - Verify that flight passengers can choose which food does they want when they will in flight.The optional can be standard, vegetarian, halal, etc. |  | 2022-03-19 | 2022-03-23
1.1.5 | Confirmation | As a passenger, I want scan my ID documents, So that I can click to confirm the check-in | 1 | 1 | - Verify that after choosing seats and food, the screen shows the passengers to scan their ID documents to conform they will check in. |  | 2022-03-29 | 2022-03-29
1.3.1 | Paper Boarding Pass | As a traditional passenger, I want a paper characteristics boarding pass So that I can get clear information without going through the tedious process of looking it up on my phone | 1 | 1 | - Verify that the boarding pass has information including flight number, airlines, destination, class level, flight date, seat number, boarding gate, passenger name, boarding time and the ID of the boarding pass - Verify that the layout is reasonable and beautiful |  | 2022-03-20 | 2022-03-20
1.2.3 | Bill Confirmation | As a Passenger with special needs I want to clearly see my extra payment list So that I can pay for that with no doubt | 2 | 1 | - Verify that the list is displayed wholly. - Verify that the list is displayed clearly. - Verify the process of paying is convenient. |  | 2022-03-23 | 2022-03-26
1.3.3.1 | Printing baggage tickets | As a airport staff I want a ticket that needs to be attached to the check-in baggage So that I can record and check the weight and contents of the luggage during the security check to ensure the safety of the flight | 2 | 1 | - Verify that the ticket has the information including the flight number, destination, departure, and the ID of the baggage tag - Verify that the layout is reasonable and beautiful |  | 2022-03-22 | 2022-03-24
1.3.3.2 | Printing baggage tickets | As a Businessman I want a ticket with the number of the assigned bag drop counter where the passenger needs to go to drop his/her check-in baggage So that I can faster access to bag drop counter information | 2 | 1 | - Verify that tickets are printed with adhesive material on the back, giving passengers the option to attach their tickets to their boarding passes without losing them |  | 2022-03-22 | 2022-03-24
1.1.2 | Login with ID | As a passenger, I want to have multiple ways to retrieve my flight booking information, So that I can continue even if I forget my booking number. | 3 | 1 | - Verify that users have the options to search their flight information in ways other than inputting booking number, such as entering surname and ID number, or scanning their ID documents. |  | 2022-03-22 | 2022-03-28
1.2.1 | Seat preferences | As a Passenger with special seating needs I want to select special seat (e.g., seat with extra legroom) So that I can stay more comfortable during the flight | 3 | 1 | - Verify that seats that can be chosen are still available. - Verify that user can see the position of seat clearly. - Verify that the additional price can be displayed. |  | 2022-03-19 | 2022-03-21
1.3.2 | Printing tags | As a passenger with a plain suitcase I want a tag that needs to be attached to the carry-on baggage So that I can find my own luggage by checking the tag on my suitcase, and the baggage won’t be taken in error | 3 | 1 | - Varify that the tag has the information including the surname of the passenger and the number of the baggage |  | 2022-03-22 | 2022-03-23
1.4 | Back-end system | As a Airline staff I want to view the list of passengers and their check-in status So that I can provide info to other departments | 3 | 1 | - Verify that the page can display real-time status. - Verify that passengers that have not checked in yet are listed on top. - Verify that special needs of passengers are attached. |  | 2022-03-25 | 2022-03-27
1.2.2 | Meal preferences | As a Passenger with special meal needs I want to select special meal (e.g., Chinese food, French food…) So that I can eat more delicious food during flight | 4 | 1 | - Verify that meal that can be chosen are available for that Airline company - Verify that sample pictures can be displayed - Verify that the additional price can be displayed. |  | 2022-03-19 | 2022-03-23
2.1 | Add I/O port config | As an airport staff I want to config the I/O port of card reader mounted on kiosk So that I can choose devices more flexible | 2 | 2 | - Verify that configuration file should be generated if not exists - Verify that user can edit configuration file |  | 2022-04-08 | 2022-04-11
2.2 | Better admin exit | As an airport staff I want to make sure that I can and only I can exit this software So that the check-in system can run safe | 1 | 2 | - Verify that the software should be killed at any circumstances - Verify that the method is hidden on screen |  | 2022-04-11 | 2022-04-11
2.3 | Show all filghts | As a passenger I want to select flights from multiple booking numbers So that I can check in any flight I booked | 2 | 2 | - Verify that all flights are displayed correctly - Verify that flight info card are categorized by booking numbers |  | 2022-04-10 | 2022-04-10
2.4 | Add planes info | As a passenger I want to know plane information when selecting seats So that I can choose the seat I like | 3 | 2 | - Verify that model, capacity and airline are included |  | 2022-04-11 | 2022-04-11
2.5 | Add animation | As a airport manager I want to equipt the software with fancy animations So that my passengers can have silky smooth experiences | 2 | 2 | - Verify that no bugs occur - Verify that the animation can run like silky chocolate |  | 2022-04-11 | 2022-04-11
2.6 | Add clock | As a passenger I want to know the current time when I use the software So that I can campare times conveniently | 3 | 2 | - Verify that the clock wouldn't stop |  | 2022-04-11 | 2022-04-11