## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
2.1.1 | Story 2.1.1 | As a passenger, I want to use my booking number to retrieve my flight booking information, So that I can check my flight information easily. | 1 | 1 | When users input their booking numb ers, the screen displays information of their flight. |  | 2022-03-18 | 2022-03-24
2.1.3 | Story 2.1.3 | As a passenger, I want select seats when I will in flight (such as: economy class, first class, etc.). So that I can have a suitable seat. | 1 | 1 | Upon successful retrieval of the booking, the system will show a summary of the booked flight. At this moment, the flight passengers can choose which seats does they want when they will in flight.The optional can be economy class, first class, etc. |  | 2022-03-19 | 2022-03-21
2.1.4 | Story 2.1.4 | As a passenger, I want to select food without breaking taboos ( such as standard, vegetarian, halal, etc.) So that I can have more suitable meat with personal dietary habit. | 1 | 1 | Upon successful retrieval of the booking, the system will show a summary of the booked flight. At this moment, the flight passengers can choose which food does they want when they will in flight.The optional can be standard, vegetarian, halal, etc. |  | 2022-03-19 | 2022-03-23
2.1.5 | Story 2.1.5 | As a passenger, I want scan my ID documents, So that I can click to confirm the check-in | 1 | 1 | After choosing seats and food, the screen shows the passengers to scan their ID documents to conform they will check in.
2.3.1 | Story 2.3.1 | As a traditional passenger, I want a paper characteristics boarding pass So that I can get clear information without going through the tedious process of looking it up on my phone | 1 | 1 | The boarding pass needs to have information including flight number, airlines, destination, class level, flight date, seat number, boarding gate, passenger name, boarding time and the ID of boarding pass |  | 2022-03-20 | 2022-03-20
2.2.3 | Story 2.2.3 | As a Passenger with special needs I want to clearly see my extra payment list So that I can pay for that with no doubt | 2 | 1 | ·Verify that the list is displayed wholly. ·Verify that the list is displayed clearly. ·Verify the process of paying is convenient. |  | 2022-03-23 | 2022-03-26
2.3.2.1 | Story 2.3.3.1 | As a airport staff I want a ticket that needs to be attached to the check-in baggage So that I can record and check the weight and contents of the luggage during the security check to ensure the safety of the flight | 2 | 1 | The ticket needs to have the information including the flight number, destination, departure, and the ID of the baggage tag |  | 2022-03-22 | 2022-03-24
2.3.3.2 | Story 2.3.3.2 | As a Businessman I want a ticket with the number of the assigned bag drop counter where the passenger needs to go to drop his/her check-in baggage So that I can faster access to bag drop counter information | 2 | 1 | Tickets are printed with adhesive material on the back, giving passengers the option to attach their tickets to their boarding passes without losing them |  | 2022-03-22 | 2022-03-24
2.1.2 | Story 2.1.2 | As a passenger, I want to have multiple ways to retrieve my flight booking information, So that I can continue even if I forget my booking number. | 3 | 1 | Users have the options to search their flight information in ways other than inputting booking number, such as entering surname and ID number, or scanning their ID documents. |  | 2022-03-22
2.2.1 | Story 2.2.1 | As a Passenger with special seating needs I want to select special seat (e.g., seat with extra legroom) So that I can stay more comfortable during the flight | 3 | 1 | ·Verify that seats that can be chosen are still available. ·Verify that user can see the position of seat clearly. ·Verify that the additional price can be displayed. |  | 2022-03-19 | 2022-03-21
2.3.2 | Story 2.3.2 | As a passenger with a plain suitcase I want a tag that needs to be attached to the carry-on baggage So that I can find my own luggage by checking the tag on my suitcase, and the baggage won’t be taken in error | 3 | 1 | The tag needs to have the information including the surname of passenger and the number of the baggage |  | 2022-03-22 | 2022-03-23
2.4 | Story 2.4 | As a Airline staff I want to view the list of passengers and their check-in status So that I can provide info to other departments | 3 | 1 | ·Verify that the page can display real-time status. ·Verify that passengers that have not checked in yet are listed on top. ·Verify that special needs of passengers are attached. |  | 2022-03-25 | 2022-03-27
2.2.2 | Story 2.2.2 | As a Passenger with special meal needs I want to select special meal (e.g., Chinese food, French food…) So that I can eat more delicious food during flight | 4 | 1 | ·Verify that meal that can be chosen are available for that Airline company ·Verify that sample pictures can be displayed ·Verify that the additional price can be displayed. |  | 2022-03-19 | 2022-03-23